## Instructions
GC/CMAR Name: |  |  | Supportive Invoices | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
GC/CMAR Pay Application #: |  |  | Vendor Name
Services start date: |  |  | Invoice ID
Services end date: |  |  | Start date of service
End date of service
Mimic the columns directly from Pay App
Line item # | Description of Work | Work completed this period ($ amount) | Invoice Totals | 1: Insert Corresponding $ Amount for Each Subcontracted Invoice for Each Line Item from GC/CMAR Pay App
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Totals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1) Enter GC/CMAR Pay App Info
2) Insert the information directly from the GC/CMAR Pay App representing the change in work completed for each budget line item for the period of work completed
3) Enter all subcontracted invoice information in this section (Use column 1 for any work completed by the GC/CMAR themselves)
4) Enter the dollar amount from each subcontracted invoice in the cell that corresponds with the correct line item from the Pay App (see "Completed Example" tab for additional clarification)
5) Ensure the totals in columns D and E match to verify all supportive documentation is accounted for

## Completed Example
GC/CMAR Name: |  | John Doe's Construction Management | Supportive Invoices | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
GC/CMAR Pay Application #: |  | 2178-Pay App 4 | Vendor Name | John Doe's C.M. | Jack's Heavy Equip. | Mtn. Flooring | Creek Construction | WY Wood | River Insulation | Plains Glass | Windy Finishes | Belts Plus | Piper's Plumbing | Sparks Electric
Services start date: |  | 2024-09-01 | Invoice ID | 2178-Pay App 4 | 2178.005 | 2178.019 | 2178.023 | 2178.007 | 2178.001 | 2178.002 | 2178.012 | 2178.008 | 2178.011 | 2178.003
Services end date: |  | 2024-10-31 | Start date of service | 2024-09-01 | 2024-09-25 | 2024-10-01 | 2024-10-01 | 2024-10-01 | 2024-09-01 | 2024-09-17 | 2024-10-01 | 2024-10-01 | 2024-09-25 | 2024-09-25
|  |  | End date of service | 2024-10-31 | 2024-10-25 | 2024-10-22 | 2024-10-25 | 2024-10-30 | 2024-09-30 | 2024-10-17 | 2024-10-31 | 2024-10-31 | 2024-10-23 | 2024-10-25
Mimic the columns directly from Pay App
Line item # | Description of Work | Work completed this period ($ amount) | Invoice Totals | 1: Insert Corresponding $ Amount for Each Subcontracted Invoice for Each Line Item from GC/CMAR Pay App
1 | General Conditions | 131731 | 131731 | 1: 131731
2 | Sitework | 82769 | 82769 | 2: 50000; 3: 32769
3 | Concrete | 0 | 0
5 | Masonry | 0 | 0
5 | Metals | 15180.28 | 15180.28 | 4: 15180.28
6 | Wood & Plastics | 67834.84 | 67834.84 | 5: 67834.84
7 | Thermal/Moisture Protection | 80000 | 80000 | 6: 80000
8 | Doors & Windows | 26200 | 26200 | 7: 26200
9 | Finishes | 26767.58 | 26767.58 | 8: 26767.58
10 | Specialties | 0 | 0
12 | Furnishings | 0 | 0
14 | Conveying Systems | 40000 | 40000 | 9: 40000
15 | Mechanical | 60000 | 60000 | 10: 60000
16 | Electrical | 68479 | 68479 | 11: 68479
40 | CMAR Contingency | 0 | 0
45 | Owner Contingency | 0 | 0
50 | General Liability | 0 | 0
55 | Builders Risk | 0 | 0
60 | P&P Bond | 0 | 0
70 | Value Analysis Allowance | 0 | 0
80 | Contractor Fee | 60372.07 | 60372.07 | 1: 60372.07
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Totals |  | 659333.77 | 659333.77 | 192103.07 | 50000 | 32769 | 15180.28 | 67834.84 | 80000 | 26200 | 26767.58 | 40000 | 60000 | 68479

## Reconciliation Sheet
GC/CMAR Name: |  |  | Supportive Invoices | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
GC/CMAR Pay Application #: |  |  | Vendor Name
Services start date: |  |  | Invoice ID
Services end date: |  |  | Start date of service
End date of service
Mimic the columns directly from Pay App
Line item # | Description of Work | Work completed this period ($ amount) | Invoice Totals | 1: Insert Corresponding $ Amount for Each Subcontracted Invoice for Each Line Item from GC/CMAR Pay App
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
|  | 0 | 0
Totals |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0